## Sheet1 (hidden)
Site Migration Checklist- https://www.demandfluence.com/
Pre-migration Planning
1 | Define objectives and goals for the migration.
2 | Conduct a comprehensive audit of the current website.
3 | Backup all website files and databases.
4 | Notify stakeholders about the upcoming migration.
5 | Set up a staging environment for testing.
Content and URL Mapping:
1 | Create a detailed inventory of all URLs and content.
2 | Map old URLs to new URLs to ensure proper redirection.
3 | Update internal links within the content.
SEO Considerations:
1 | Perform keyword research for new URLs if necessary.
2 | Update meta tags, titles, and descriptions for SEO optimization.
3 | Implement 301 redirects for old URLs to maintain SEO equity.
Technical Setup:
1 | Choose a reliable hosting provider for the new website.
2 | Install necessary software and plugins for the new platform.
3 | Set up SSL certificates for secure browsing.
4 | Configure server settings for optimal performance.
Testing Phase:
1 | Conduct extensive testing of the new website's functionality.
2 | Test all forms, links, and interactive elements.
3 | Verify responsiveness across different devices and browsers.
4 | Check for any broken links or missing assets.
Launch and Post-migration Tasks:
1 | Schedule the migration during off-peak hours.
2 | Monitor website performance closely after the migration.
3 | Verify that all redirects are working correctly.
4 | Update XML sitemap and submit to search engines.
5 | Notify users and stakeholders about the successful migration.
Performance Monitoring:
1 | Monitor website traffic, load times, and user interactions post-migration.
2 | Address any performance issues promptly.
3 | Continuously optimize the website for better performance and user experience.
Backup and Security:
1 | Regularly backup website files and databases.
2 | Implement security measures to protect against cyber threats.
3 | Stay informed about security updates and patches for the website platform.

## Guidelines for Migration
S. No. | Pre-Migration Phase | Redesign and Development Phase | Staging and Testing Phase | Launch Phase | Post-Launch Monitoring
1 | Create a Full Backup of the Old Site | Create a URL Mapping Plan | Test on a Staging Site | Monitor Google Search Console | Monitor Keyword Rankings
| > Ensure the entire website, including databases and files, is backed up for recovery if needed. | > Map old URLs to new ones if the structure changes. > Aim to keep the URL structure consistent for top-ranking pages. | > Review the new site on a staging environment to ensure no broken links or missing content. | > Re-submit the sitemap with the new structure. > Check for crawl errors and fix any 404s. | >Track rankings daily for at least a month to spot and address any drops.
2 | Benchmark Current SEO Performance | Transfer Metadata | Check Robots.txt and Meta Tags | Verify Analytics Tracking | Audit Organic Traffic
| > Record keyword rankings, organic traffic, bounce rates, and key pages in Google Analytics and Search Console. | > Ensure titles, meta descriptions, alt tags, schema markup, Canonical from the old site are applied to the new one. > Create document and send to Developer for implementation | > Ensure the staging site is blocked from indexing by search engines. | > Ensure Google Analytics, Google Tag Manager, and any other tracking scripts are functioning on the new site. | > Compare pre-launch and post-launch organic traffic in Google Analytics.
3 | Crawl the Old Website | Set Up Redirects | Verify Redirects | Test Redirects Again | Check Backlinks
| > Use tools like Screaming Frog or SEMrush to crawl the site and create a detailed URL map, including metadata, page titles, and internal links. | > Implement 301 redirects for all old URLs to corresponding new URLs. > Test redirects to confirm they point to the right pages. | > Use tools like Screaming Frog to test all redirects from the old site to the staging site. | > Conduct another test to verify all 301 redirects are working post-launch. | > Ensure backlinks pointing to old URLs are correctly redirected to new URLs.
4 | Export Key SEO Data | Optimize for Mobile and Speed | Fix Technical SEO Issues | Check Canonical Tags | Fix Any Indexing Issues
| > Export on-page data (titles, meta descriptions, alt tags). > Download backlinks from Search Console or Ahrefs. > List top-performing pages in terms of traffic and conversions. | > Ensure the new design is mobile-friendly and optimized for speed (use Google PageSpeed Insights). | > Validate no broken links, duplicate content, or crawl issues. | > Ensure canonical tags point to the correct pages to prevent duplicate content issues. | Regularly check Search Console for coverage errors and address them immediately.
5 | Conduct a Content Audit | Ensure On-Page SEO |  |  | Communicate with Search Engines
| > Identify high-performing pages that must be retained. > Plan updates for underperforming content and consolidate redundant pages. | > Retain existing H1s, internal links, and keyword placement. > Avoid adding noindex or nofollow tags unintentionally |  |  | > Use the "URL Inspection" tool in Google Search Console to validate and request reindexing of key pages.
Monitor User Behavior
Track bounce rates, session durations, and conversion rates to ensure the new design hasn’t negatively impacted user experience.
Staging and Testing Phase

## Checklist
| Check the following onpage points for Every Webpage | Status | Document Attached
1 | Meta Title | Done | https://docs.google.com/spreadsheets/d/1lm0K66bFpzM6uJls08fmEoVcqNtQS23wXS-o5Z2fkSw/edit?gid=0#gid=0
2 | Meta Description | Done | https://docs.google.com/spreadsheets/d/1lm0K66bFpzM6uJls08fmEoVcqNtQS23wXS-o5Z2fkSw/edit?gid=0#gid=0
3 | H1 to H6 | Done | https://docs.google.com/spreadsheets/d/1lm0K66bFpzM6uJls08fmEoVcqNtQS23wXS-o5Z2fkSw/edit?gid=0#gid=0
4 | Alt Tags | No Done | After website is live
5 | Canonical tags | Done | same as main url
6 | Check every page content | Done | Content Should be same
7 | Internal links | Done | Other Products section
8 | FAQs | Done | https://docs.google.com/document/d/1HdN9OoyUs5n2i2_BZ6oovH5sTQ6VqIELXJq-PG3J9lw/edit?tab=t.0
9 | All Schemas( Organization, Local, FAQ Schema) | Done | https://docs.google.com/document/d/1HdN9OoyUs5n2i2_BZ6oovH5sTQ6VqIELXJq-PG3J9lw/edit?tab=t.0
10 | Images | After Migration | After Migration
11 | Every Page Speed check on new site | Sudeep | Sudeep will do this
12 | Google Tag Manager Code should be implemented on the staging and after live | Sudeep | Sudeep will do this
13 | Microsoft clarity code | Sudeep | Need to add new code for this
14 | Test Contact forms | Sudeep | Sudeep will do this
15 | Check Thank you Page | Done | https://secure-house.co.uk/thank-you/
16 | Check GTM Code on Thank you page | Not Done | Sudeep will do this
17 | Test every form should have thank you page on website | Not Done | Sudeep will do this
18 | Blog Page | Not Done | Due to Malware attack we did not find any blog pages but on staging site we will give all the blog content to post with the same url
19 | Internal Blogs Onpage | Not Done | Due to Malware attack we did not find any blog pages but on staging site we will give all the blog content to post with the same url
20 | Sitemap of website | Done | https://secure-house.co.uk/sitemap_index.xml https://secure-house.co.uk/post-sitemap.xml https://secure-house.co.uk/post-sitemap2.xml https://secure-house.co.uk/avada_portfolio-sitemap.xml https://secure-house.co.uk/category-sitemap.xml https://secure-house.co.uk/post_tag-sitemap.xml https://secure-house.co.uk/fusion_tb_category-sitemap.xml https://secure-house.co.uk/portfolio_category-sitemap.xml https://secure-house.co.uk/element_category-sitemap.xml https://secure-house.co.uk/slide-page-sitemap.xml https://secure-house.co.uk/author-sitemap.xml
21 | Robots.txt File | Done | User-agent: * Disallow: /wp-admin/ Allow: /wp-admin/admin-ajax.php Host: secure-house.co.uk Sitemap: https://secure-house.co.uk/sitemap_index.xml https://secure-house.co.uk/robots.txt
22 | Download Brochure , CTA buttons